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Arapahoe Road and Jordan Road Intersection Reconstruction
JULY 2014


In May of this year, Hamon Contractors began work on the CDOT Arapahoe Road Resurfacing Project.  This project includes the mill and overlay of Arapahoe Road from Boston/Clinton to Parker Road.  The reconstruction of the Arapahoe Road and Jordan Road intersection will begin on Friday, July 25, 2014 at midnight and will be aggressively scheduled for 20 days of major impacts to ensure the entire project completes by October 2014.  

The reconstruction work at the intersection of Jordan Road and Arapahoe Road will consist of replacement of the current asphalt pavement with concrete pavement.  Included in the scope of the project are new islands, a mill and overlay of the asphalt leading up to the intersection, and new traffic signals that will allow a double left turn from WB Arapahoe onto SB Jordan Road.  

Project Schedule and Closures

During this 20 day period the intersection will have 24-hour construction periods where left turns and Jordan Road thru traffic will not be allowed.  The work will be completed in three phases with the duration of each phase to range between five to seven calendar days. 
Phase I will begin on Friday July 25th at midnight and Phase 3 is expected to be completed by August 15th. Phase 2 will have the most restrictive movement with no left turns on any leg of the intersection and no thru movements on northbound and southbound Jordan Road.  Pedestrian access will be eliminated or limited during this time.
Traffic / Noise Impacts

During the 20-day reconstruction of the intersection, traffic operations and movements will be limited as detailed below (a map of the intersection is included for reference):  

Phase 1 – Eastbound and westbound Arapahoe Road will provide designated left turn lanes onto northbound and southbound Jordan Road, respectively; two through lanes; and one shared through/right.  Northbound and southbound Jordan Road will provide a designated left turn lane, a through lane, and a right turn lane.  

Phase 2 – No left turns allowed on any leg of the intersection and through movements on Jordan Road will be prohibited.  Eastbound and westbound Arapahoe Road will provide two through lanes and one shared through right.  During this time period, the gate at the Valley Country Club Estates will be open for residents north of Arapahoe Road.  The date for this phase will be around July 29th, depending on progress and weather.
Phase 3 - Eastbound and westbound Arapahoe Road will provide designated left turn lanes onto northbound and southbound Jordan Road, respectively; two through lanes; and one shared through/right.  Northbound and southbound Jordan Road will provide a designated left turn lane, a through lane, and a right turn lane.  
Slow for Cone Zone

The Colorado Department of Transportation and Hamon Contractors appreciate motorists’ patience and attentiveness when driving through the project construction zone. We ask motorists’ to slow down for cone zones.
Questions?

If you have any questions or concerns regarding the project, please contact Hamon Contractors, Inc’s Public Information line at (303) 419-4903. A representative will return your call within 24 hours.  More information can be found on the CDOT project website 

www.coloradodot.info/projects/
arapahoeresurfacing

In case of an emergency, the Hamon Project Engineers name is Dan Aupperle. His phone number is (303) 901-7082.  You may also contact Aja Mills at (720) 315-8085. 
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"Note: The movement arrows shown above represent existing conditions, and are only shown as a guide."  
Hamon Contractors, Inc.
(303) 297-0340
www.hamoncontractors.com
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